## 1. Overall plan
CCDM overall implementation plan | [5 empty] | Last Updated: |  |  | By:
What | This worksheet is a template for documenting the master plan for implementing CCDM across all services
Who | The SSHW Programme Consultant completes worksheet in collaboration with the AH lead, CCDM Site Coordinator and Co-chairs.
How | Complete the table below using the key colour and associated abbreviation for the work e.g. Data collection = DC (see more abbreviations below)
Use these documents for planning - CCDM programme standards, road maps, VRM tools
Document the hospital-wide plan for data collection (DC), CCDM governance (Council, LDC), core data set (CDS) and variance response management (VRM).
Document the plan for implementing local data councils, core data set, data collection and VRM for each service
Consider sequencing that is needed i.e. some things need to come before others e.g. software upgrades, resource to respond before variance response management etc.
Factor in time to establish standard operating procedures for business as usual.
Discuss the draft with Co-chairs. Submit to CCDM council for endorsement
When | Complete at the beginning of programme implementation. Review and update at least annually.
|  |  | Key: |  |  |  |  | BAU | On hold | No data collection tool(s)
|  |  |  | Planned | In progress | Completed | Not done | Business as usual
|  |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
DHB wide/Hospital site | Service | Standard | Key milestone | Jan-20 | Apr-20 | Jul-20 | Oct-20 | Jan-21 | Apr-21 | Jul-21 | Oct-21 | Jan-22 | Apr-22 | Jul-22 | Oct-22 | Jan-23 | Apr-23 | Jul-23 | Oct-23
DHB | N/A | 1. Governance | CCDM council meets AH needs
DHB | N/A | 1. Governance | AH working group operational
DHB | N/A | 2. Staffing methodology | Required data collected and accurate
DHB | N/A | 3. Core data set | Core data set implemented
DHB | N/A | 4. Variance response management | Variance response management operational

## 2. Annual plan 20YY-20YY
CCDM programme annual plan |  |  | Last updated: | By:
What | This worksheet is a template for documenting the annual plan for implementing CCDM. It is taken from the master plan.
Who | The SSHW Programme Consultant completes worksheet in collaboration with the AH lead, CCDM Site Coordinator and Co-chairs.
How | Rename worksheet Annual plan 20YY-20YY. For subsequent years create a new worksheet.
Complete the table below using the key colour and text.
Take the selected year from the Overall plan and document it in more detail below.
Use these documents for planning - CCDM programme standards, road maps, VRM tools for programme implementation.
Hide inactive rows i.e. rows where there is no activity in the current year.
Consider sequencing i.e. consider wider DHB activity so AH plan dovetails with overall planning
Factor in time to establish standard operating procedures for business as usual.
Discuss the draft with Co-chairs. Submit to CCDM council for endorsement.
Report on progress against the plan to CCDM council/working group as required.
When | Complete as per the road map. This is a live document. Update progress against plan at least monthly.
|  |  | Key: | P | IP | C | <30 | 30-60 | >60
|  |  |  | Planned | In progress | Completed | Less than 30 days over | 30-60 days over | greater than 60 days over
Standard | No. | Main steps | Resource required | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Governance | 1 | DAHST (or appropropriate proxy) is a member of CCDM council
1. Governance | 2 | PSA rep is a member of CCDM council
1. Governance | 3 | Complete AH workshops for the council (if required)
1. Governance | 4 | Complete AH workshops for AH leads / staff
1. Governance | 5 | AH Working Group established with Terms of Reference
1. Governance | 6 | Complete stocktake assessment
1. Governance | 7 | Write & agree workplan
1. Governance | 8 | Establish sub working groups if required (if large DHB, multiple sites)
1. Governance | 9 | Monitor & report against workplan/s
1. Governance | 10 | Establish AH rep on ward Local Data Councils
1. Governance | 11 | Establish AH Data Quality Group with Terms of Reference (if separate from Working Group)
2. Staffing methodology | 12 | AH are using an activity data collection tool / system (s)
2. Staffing methodology | 13 | Clinical data is captured
2. Staffing methodology | 14 | Non clinical data is captured
2. Staffing methodology | 15 | Unmet need is captured
2. Staffing methodology | 16 | Staffing capacity data is captured
2. Staffing methodology | 17 | AH represented on TC (or other) steering group
2. Staffing methodology | 18 | AH TrendCare User Guide operationalised (if appropriate)
2. Staffing methodology | 19 | Data quality guideline agreed and implemented
3. Core data set | 20 | Complete AH CDS workshop
3. Core data set | 21 | Undertake core data set stocktake
3. Core data set | 22 | Agree roll out plan
3. Core data set | 23 | Write & agree detailed workplan
3. Core data set | 24 | Agree & document process for business as usual
3. Core data set | 25 | Agree layout
3. Core data set | 26 | Commence data collation
3. Core data set | 27 | Review, report & improve measures
4. Variance response management | 28 | Complete AH VRM workshop
4. Variance response management | 29 | Review VRM stocktake
4. Variance response management | 30 | Write & agree detailed workplan
4. Variance response management | 31 | Implement tools and processes
4. Variance response management | 32 | Establish reporting mechanisms

## 3. Detailed workplan
CCDM detailed workplan |  | Last updated: | By:
What | This worksheet is a template for documenting the weekly plan for implementing CCDM. It is taken from the annual plan.
The detailed workplan is a key project management tool.
Who | The SSHW Programme Consultant completes plan in collaboration with the CCDM Site Coordinator. The Coordinator maintains the live document.
How | Rename worksheet tab 'Detailed workplan xx directorate/service/ward'. Create a new worksheet for each.
Complete the table below using the key colour and text.
Take the Annual plan and document it in more detail below. If needed, use a printed road map for visual re-inforcement of the process.
Hide inactive rows i.e. rows where there is no activity in the current year.
Use the detailed plan to populate the monthly status report.
When | Review and update the status weekly.
|  |  | Key: | P | IP | C | <30 | 30-60 | >60
|  |  |  | Planned | In progress | Completed | Less than 30 days over | 30-60 days over | greater than 60 days over
Week
Component | Main steps | Actions | By who | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
CCDM governance
CCDM governance
CCDM governance
CCDM governance
CCDM governance
CCDM governance
Staffing methodology
Staffing methodology
Staffing methodology
Staffing methodology
Staffing methodology
Staffing methodology
Core data set
Core data set
Core data set
Core data set
Core data set
Core data set
Variance Response Management
Variance Response Management
Variance Response Management
Variance Response Management
Variance Response Management
Variance Response Management
Variance Response Management
Note on C16: Colette Breton: Includes actions from roadmap & workshops
Note on D16: Colette Breton: Who is doing the action

## 4. Monthly status report
What | This worksheet is a template for documenting the monthly status report for the CCDM council.
The status report is taken from the detailed workplan/s.
Who | The CCDM Allied Health lead completes status report
How | Fill in the blanks below and/or overtype each month.
Copy and paste actions from the detailed workplan from that month into the completed column.
Copy and paste items from the detailed workplan for the following month into the planned column.
Complete the traffic light for scope, schedule and risks. Colour boxes as appropriate.
Exception report on risks and issues at the bottom of the page.
Hide - what, who, how, when rows. PDF the status report and save with month and year in the file name.
Distribute the status report with the monthly CCDM council agenda.
When | Complete every month for the previous month.
Date: | Completed by: | Status:
Component | Completed | Planned | Comments
CCDM governance
CCDM governance
CCDM governance
Staffing methodology
Staffing methodology
Staffing methodology
Core data set
Core data set
Core data set
Variance resonse management
Variance resonse management
Variance resonse management
Risks/Issues:
Scope
Schedule
Risks
CCDM monthly status report